## Sheet1
Gannt chart construction
|  |  |  | Week 1 | [7 empty] | Week 2 | [6 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | week 10 | [6 empty] | week 11 | [6 empty] | Week 12
[5 empty] | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | thu | fri | sat | sun | mon | tue | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thur | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun
Task number | Task | Duration | Predecessor |  | 1 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | foundation and drainage | 2 weeks | bar: mon 1 to fri 31; Week 2 mon 3 to Week 2 fri 7
2 | steel frame | 2 weeks | 1 | bar: Week 3 mon 10 to Week 3 fri 13; Week 4 mon 16 to Week 4 fri 19
3 | brickwork and roof | 3 weeks | 2 | bar: Week 5 mon 22 to Week 5 fri 26; Week 6 mon 30 to Week 6 fri 3; Week 7 mon 6 to Week 7 fri 10
4 | building inspection | 2 days | 3 | bar: Week 8 mon 13 to Week 8 tue 14
5 | internal works | 2 weeks | 3 | bar: Week 8 mon 13 to Week 8 fri 17; Week 9 mon 20 to Week 9 fri 25
6 | external windows and doors | 1 week | 5 | bar: week 10 mon 28 to week 10 fri 1
7 | decoration | 1 week | 6 | bar: week 11 mon 4 to week 11 fri 8
8 | fixtures and fittings | 1 week | 3 | bar: Week 12 mon 11 to Week 12 fri 15