## Sheet1
Creating a comic (Rachel recycle )
task number | task | duration | predecessors | week 1 | [6 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 4
|  |  |  | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun
1 | outline story | 4 days | bar: week 1 mon to week 1 thu
2 | script | 3 days | 1 | week 2 tue: 2
3 | story board | 4 days | 1 | week 3 mon: 3
4 | video discussion | 1 day | 3 | week 3 tue: 4
5 | create backgrounds | 3 days | 3 | week 3 fri: 5
6 | create speech bubbles | 3 days | 1 | week 4 mon: 7
7 | council review | 1 day | 6 | week 4 thu: 8
8 | printing the comic | 1 day | 7 | week 4 fri: 9